## Slide 1
State, Local, Tribal Tiger Team 90 Day Proposal
Co-Chair- Cait Ryan,
IRIS Health Solutions
Co-Chair- Tom Carlson
Tom Carlson Consulting
Notes: During the NBAC Face to Face meeting in October 2019, the request was made to stand up a State, Local, and Trbal Tiger Team in order to expand NIEM’s reach/users. This team will leverage the pre-existing work of the past State and Local Tiger team.
This presentation is meant to provide a tentative overview and timeline of the foreseeable future and deliverables. It is our understanding that this likely will change once meetings are underway.

## Slide 2: Deliverables
Charter
Tiger Team
GitHub Page
Marketing Materials
Outreach Opportunities Tracker
Grant Assistance
NIEM Virtual Roadshow
Notes: The most important deliverables that can be addressed over the next 90 days are:
The development and execution of a Project Charter
The establishment and hosting of a Tiger Team
The establishment and development of an Online GitHub Page through the NIEM MO
The production of an Outreach Opportunity List that will help us to identify conferences, meetings, symposiums that the tiger team should attend and/or present at.
The production of marketing materials tailored to the needs of the Tiger Team and the audience it is trying to reach.
Provide assistance to organizations with grant application and execution assistance.
The development of a “NIEM Virtual Roadshow”

## Slide 3: Technology
TT WEBSITE/PAGE
NIEM GitHub
MEMBER COLLABORATION
Google Docs
WEBINAR CAPABILITIES
NIEM MO WebEx
Notes: We’ve identified the following technologies to facilitate hosting and management of the Tiger Team
Leverage existing NIEM GitHub site for Tiger Team web presence
Leverage GoogleDocs as current NIEM MO Collaboration Hub is not practical for current work environment and block access for several TT members due to strict access requirements
Leverage the NIEM MO program’s webinar hosting service (WebEx)

## Slide 4: 90 Day Timeline
30 Days
60 Days
90 Days
Attend/Present at Outreach Opportunities
Establish GitHub Page
Host Kickoff Meeting
Develop Outreach Opportunities Tracker
Catalogue Existing Marketing Materials
Establish Meeting Logistics
Follow Up from Outreach Opportunities
Continue Hosting and Growing TT
Plan “NIEM Roadshow Series"
Host “NIEM Roadshow”
SLT TT promotion
Finalize Charter
CHECKPOINT
CHECKPOINT
Notes: This is a brief look at the activities we plan to accomplish over the next 90 days

## Slide 5
PROMOTE SLT TT
Leverage NIEM MO Channels
  Ask for 2+ representatives from each domain
  Members of NIEM MO
Identify Outside Communications NIEM- SLT reps
  Identify in first few SLT TT meetings
Announce in NIC groups, LinkedIn
ESTABLISH GITHUB PAGE
Work with NIEM MO to stand up page on GitHub
  TT deliverables, meeting materials, meeting invites, reference docs
ESTABLISH MEETING LOGISTICS
Webinar Platform- Zoom
Collaboration Platform- Google Docs
Meet 1x a week, 1 hr.
HOST KICKOFF MEETING
Review TT Charter
Review TT Membership and ID additional invitees
30
Days
Notes: First we will produce a “call to action” email and flyer and leverage the NIEM MO marketing channels to promote participation in the new TT. We will also ask for NBAC and NIEM MO participation and recommendations of who should participate.
Once established, the Tiger Team will look to outside participation based on individuals contacts and associations
We will work with the NIEM MO to stand up a GitHub page to host TT final deliverables, meeting materials, and helpful resources and referenced documents.
We have determined that zoom will be used to host virtual meetings, unless we are able to use the NIEM MO’s WebEx. All meetings will be recorded and uploaded to the GitHub Page. Meeting minutes will be taken and posted to the GitHub page within 48 hours of meeting. The Tiger Team will meet 1x a week, for 1 hour.
The first few TT meetings will focus on finalizing the charter and forming the group, making sure we are inviting the right people.

## Slide 6
60
Days
FINALIZE CHARTER
  Work through Charter during TT Meetings
  Post final product on GitHub Page
CATALOGUE EXISTING MARKETING MATERIALS
  Review marketing materials
    “group” into presentation type audience
  Edit materials to suit TT needs
DEVELOP “OUTREACH OPPORTUNITIES” TRACKER
  Begin to Identify Outreach Opportunities
    Conferences, meetings, etc.
    Should TT attend and/or present
    If presenting, determine presentation to use
Notes: The TT will review marketing materials and determine
1- if they need to be edited to be tailored to the needs of the TT
2- Group into presentation types so that they can be easily identified and used at upcoming speaking engagements
The Tiger Team will search for and identify outreach opportunities, this includes conferences, webinars, meetings, symposiums, briefings, etc., that are of relevance to NIEM and the TT goals. For each event we will determine at what capacity we will participate. If it is decided that the TT should present we will designate a presenter and the presentation they will give.

## Slide 7
90
Days
ATTEND/PRESENT AT OUTREACH OPPORTUNITIES
FOLLOW UP FROM OUTREACH OPPORTUNITY
  Provide out-brief to the TT
  Follow up with organizations
  Blog post and/or summary write up for GitHub Page
  Provide updates at NBAC meetings
CONTINUE TO HOST AND GROWING THE TIGER TEAM
Notes: Once the TT begins attending and presenting at outreach opportunities the individual(s) who attended will provide an outbrief to the TT at the next TT meeting to include key talking points, lessons learned, interested parties, additional outreach opportunities, engagements, etc.
This information will be synthesized and posted in some form to the GitHub page as well as presented to the NBAC
The TT will continue to meet on a regular basis; it will continue to look for outreach opportunities, new members, identify gaps in communication efforts and produce deliverables as needed.

## Slide 8: Outreach Opportunity Register At-a-Glance
Title | Host Org. | Date | Location | Type | Cost | Priority | Audience | TT Capacity | Presenter | Presentation | Contact Person | Approval Status
Go with the Data Flow | IRIS Health Solutions | 2020-10-18 | IRIS Health Solutions | InPersn/Virtual | $50 in person; FREE Virtual FREE Present | HIGH | Fed/Prvt Sector, SLT, Various Domains | Present | Cait Ryan | Potential of Healthcare with NIEM | Cait Ryan | Pending
Let’s Get Technical | Nat’l Interop Collaborative | Weekly, Fridays | Virtual | Virtual | FREE | HIGH | Fed/Prvt Sector, SLT, Various Domains | Present | Tom Carlson | NIEM’s Impact on Cross State Interoperability | Paul Wormelli | APPROVED R. Oconnell 2020-03-24
Secure My Data Conference | NIST | 2020-08-13 | NIST HQ Gaithersburg, MD | BOTH | FREE | HIGH | Fed/Prvt Sector, SLT, Various Domains | Attend |  |  |  | APPROVED R. Oconnell 2020-03-24
My State is Better than Yours | NY Dept. of Health | 2020-10-23 | NYC, Rockefeller Conf. Hall | Both | $250 in person; $100 Virtual | HIGH | State Dept of Health, Local Dept of Health | Present | Cait Ryan | Potential of Healthcare with NIEM | Marsha Brady | REJECTED
This will be a living document on Google Drive
It will be managed by TT Co-Chairs
All TT members will have view access
NIEM-MO will be alerted when there are items for their approval
E X A M P L E O N L Y

## Slide 9: Success Metrics
New NIEM Participants
  New SLT individuals joining COI Discussions
  New SLT individuals inquiring about Domains
  New SLT Individuals joining Domains
New SLT TT Members
# of Speaking Engagements for TT
Representation from all 50 States
Notes: Success will be measured and tracked based on these criteria.

## Slide 10: Thoughts?
Co-Chair- Cait Ryan, caitcryan@irishealthsolutions.com
Co-Chair- Tom Carlson, tom@tomcarlsonconsulting.com